## DOE Projects
District/Location | School/Project | Permit No. | Issued Permit Date | Status | Scope
St. Thomas | Lockhart Elementary School | BP0532-26 | 6/15/2026 | No inspection on record | Roof repairs, interior renovations, restrooms, and flooring
St. Thomas | Yvonne E. Miliner-Bowsky Elementary School | BP0520-26 | 3/4/2026 | No inspection on record | CTE spaces, classrooms, collaboration spaces, mechanical yard, and associated parking lot
St. Croix | STX Educational Complex High School | BP0280-26 | 5/26/2026 | Work started-Phase 1
St. Croix | St. Croix Central High School | BP0484-26 | 2026-06-15 | Work Started-Phase 1 Demo/ staging area | Repairs roof, interior walls, ceilings, floors, windows, doors, painting, electrical, plumbing, mechanical, cistern, pump room, bathrooms, drainage, casework, countertops, fire system and technology system, also Construction Trailer/fencing for staging area
St. Croix | Arthur A. Richards PreK-8 School |  |  | Waiting for Contractor to schedule Final Inspections, 1st inspection scheduled for 7/15/26 | Construct eleven one- and two-story buildings including gymnasium, theater, administration building, JROTC facility, classroom spaces, cistern, and parking lot
St. Thomas | Bertha C. Boschulte Middle School | EP0177-26 | 3/17/2026 | No inspection on record | Temporary power for construction office for school repairs
St. Thomas | Bertha C. Boschulte Middle School | BP1616-25 / EC | 2/17/2026 | No inspection on record | New MEP systems, exterior facade, structural repairs and upgrades, new roof, interior reconfiguration, and interior finish upgrades
St. Thomas | Charlotte Amalie High School | BP1485-25 | 2026-03-04 | Work Started-Phase 1 Demo/ staging area | Construction of 3 story academic forts include: CTE spaces, classrooms, collaboration spaces, mechanical yard, and associated parking lot