## Sheet1
Change Order Number | Date | Description | Cost increase
Original Contract
1 | 2015-01-01 | Revise contract per Governor Mapp | 0
2 | 2016-01-01 | Archeological testing required by VISHPO | 0
3 | 2025-01-16 | Additional Archeological testing required by VISHPO | 0
4 | 2017-02-01 | Surcharge testing | 0
5 | 2025-02-17 | Revise SOV to reflect Surcharge testing
6 | 2018-01-01 | Surcharge testing after Maria | 0
7 | 2018-04-01 | Locate existing utilities | 0
8 | 2018-09-01 | Design pile foundation and install test piles | 0
9 | 2018-12-01 | Phase II Archeological testing | 0
10 | 2019-02-01 | Change foundation to pile foundation | 0
11 | 2019-07-01 | Revise design for budget reasons | 0
12 | 2025-07-19 | Extend time due to Irma/Maria | 0
13 | 2020-06-01 | Revise budget for new design per Governor Bryan | 7000000
14 | 2021-11-01 | Memorialize agreed budget Supplemental Contract | 0
15 | 2021-12-01 | Time only for FEMA floodway issues | 0
16 | 2022-11-01 | Revise PEJ and TM bleachers from aluminum to concrete | 0
17 | 2023-06-01 | Change all interior walls from studs to block | 0
18 | 2023-10-01 | Add time for bleachers and sewer relocation | 0
19 | 2024-01-01 | Add design changes via supplemental Contract 2 per Act 8781 | 5124000
20 | 2024-02-01 | Time only to allow for processing of design changes costs | 0
21 | 2024-03-01 | Memorialize agreed budget Supplemental Contract per Act 8781 | 0
22 | 2025-01-25 | Time increase while assessing FEMA Floodway delays | 0
23 | 2025-02-25 | Partial time increase due to FEMA Floodway delays | 0
24 | Pending | Time increase to finalize FEMA floodway delays | 0
Supplemental Contract 1
1 | 2022-11-01 | Revise PEJ and TM bleachers from aluminum to concrete | 0
2 | 2022-11-01 | Add storage under TM concrete bleachers | 0
3 | 2023-06-01 | Time only for design revision and partial FEMA Floodway delays | 0
5 | 2023-10-01 | Change all interior walls from studs to block | 0
6 | 2024-03-01 | Memorialize agreed budget Supplemental Contract per Act 8781 | 0
7 | 2025-02-25 | Partial time increase due to FEMA Floodway delays | 0
8 | Pending | Time increase to finalize FEMA floodway delays | 0
Supplemental Contract 2
1 | Pending | Time increase to finalize FEMA floodway delays | 0